## Action Log
St Bride's School & Nursery Parent Council - Rolling Action and Decision Log
A rolling action log is maintained of all actions arising or pending from each of the previous meetings. The status of Actions are categorised as follows:
Task complete - to be removed from listing
No identified risk, on target for completion date
Target completion date extended to allow flexibility
Target completion date unattainable, further explanation provided
Minute Ref | Meeting Date | Action | Action Owner | Due Date | Completion Date | BRAG status | Position Statement | Supporting Documentation
PC01 | 06.03.2024 | LT provided update via monthly HT report | LT
PC02 | 06.03.2024 | JH provided update regarding PC finance position and completion of Bank signatory forms now updated | JH | 05.06.2024 |  |  | JH advised current funds in PC bank account is £2600. Discussion took place around maintaining this to allow continued support to school requests and PC events.Bank signatory forms updated and previous signatories to be removed which JH/NE will undertake 01.05.24 JH advised this action will be completed by the end of this week
PC03 | 06.03.2024 | PC Church Rep to be appointed | PF/LR | 05.06.2024 |  |  | PF/LR to speak with Fr Morton on 10.03 to understand requirements 01.05.2024 LR and PF spoke with Fr Morton who advised that the Rep is of his choosing and that he would advose in due course. PJ suggested an individual from the church community who may be interested, she will speak with them and as that they make contact with Fr Morton
PC04 | 06.03.2024 | PC confirmed Easter Bonus Ball initiative which will run during Parent Reporting Evening on 2103.2024. LT advised Nursery school will also support the sale of this. PC requested this is publicised via school X (Twittter) and Parent Portal | PF/LT | 01.05.2024 |  |  | PF to provide Bonus Ball sheets to LT for Nursery sales and PC will pick up from office on Parent Reporting Evening for school parents/carers participation 01.05.2024 Easter Bonus Ball generated £231 with the lucky winner sharing half of the winnings (notified)
PC05 | 06.03.2024 | P1 New Entrant Session (21/29/05.2024) PC advised they would be present to share Parent Council information. PF can cover with PJ to confirm. PF to update PC Flyer for distribution. PC also suggested distribution to parents on first day of new term small welcome pack of tea/bag/biscuit and poem which was agreed | PF/PJ | 05.06.2024 |  |  | PF to update PC Flyer for New Entrant Session. PC to purchase parent welcome pack 01.05.2024 PF has updated Parent Council Flyer to share at the forthcoming P1 New Entrant session, this will distributed along with information on 'my nmae tags' initiative. PF asked LT if the PC Board could also be in view for the session. PF will purchase the welcome pack components for the start of the new term in due course
PC06 | 06.03.2024 | PC Banner request was discussed which would be visible in events with LT advised SLC could assist. | LT | 05.06.2024 |  |  | LT to provide contact details for PC to pursue 01.05.2024 The banner design has been drafted and will be submitted at the end of this week for printing. NE is liaising with SLC to have it printed with the expected turnaround time a few days, the intention is for this to be visible at the forthcomg P1 New Entrant session
PC07 | 06.03.2024 | End of Term Disco - PC confirmed this event for 12.06.2024 with a beach theme, children can come dressed in shorts and t-shirt. Photobooth and DJ to be booked. PF to provided disco flyer to share on school/PC social media and Parent Portal. Tuck shop and balloons to be ordered | PF/PJ/JH | 05.06.2024 |  |  | PJ to order Tuck shop/balloons for balloon arch and Photobooth. JH to book DJ 01.05.2024 DJ and Photobooth confirmed as booked. PJ will purchase Tuck Shop requirements with the inclusion of ice poles this time as the hall is usually very warm along with balloons for the balloon arch. PF to purchase some decorations and has provided disco flyer to HT which will be shared on Parent Portal and social media.
PC08 | 06.03.2024 | School Sports Day (05.06.2024) - PC confirmed Cake sale (if the weather is warm ice lollies to be included) in the AM session with flyer to be provided to school for social media/Parent Portal with inclusion of request for parents/carers to hand in items for sale. If the weather is wet these can be sold within school. | PF | 05.06.2024 |  |  | PF to provided Bake Sale Flyer to LT to share on school social media/Parent Portal with the inclusion of the caveat around the weather 01.05.2024 Bake Sale poster was shared with HT. Discussion took place around procuring some cakes/biscuits from local shops (Morrisons) or organisations (Greggs/Tunnocks) LR and PF to make contact
PC09 | 06.03.2024 | End of term ice cream van - PC suggested they purchase ice lollies rather than the use of the ice cream van to keep cost down however, it was agreed that the van was a nice end of term treat. PC to contact some ice van sellers for costing/availability including the one used at Halfway Fireworks. Total school number including staff 380. | LR | 01.05.2024 |  |  | LR to obtain numbers and contact for costs 01.05.2024 Ice cream van booked for Friday 21 June 0930-1130
PC11 | 06.03.2024 | PC Board - PC welcomed the use of a school notice board to promote the PC and it's current committee members, there will also be an update to the Nursery noticeboard to support | LR | 05.06.2024 |  |  | LR will work on designing this with the inclusion of PC committee members photographs and collect school board and update Nursery board 01.05.2024 LR completed a moveable notice board, PC requested this is visible in school at all times to promote the Parent Council and aid with faces to names of committee members. The Nursery notice board still requires a poster to be created - PF/LR to work on
PC13 | 06.03.2024 | PC Social Media - the group updated LT on the new PC logo and advised they are in the process of setting up a new Instagram page, this along with X (Twitter) they hope to further share and promote to enable parent/carer news/updates. All paperwork will carry the logo along with the school/nursery logo | PF | 05.06.2024 |  |  | PF to update and share in conjunction with IT support from Mrs Dickson 01.05.2024 PF met with Mrs Dickson who provided social media support, some password issues meant another meeting to take place to progress
PC14 | 06.03.2024 | School Lottery Proposal - PC advised of School Lottery proposal that other local schools patriciate in. The information pack was shared with HT and PC will also share the details in their update in the a forthcoming HT newsletter with a doodle poll for feedback | PC/PF | 04.09.2024 |  |  | PF to include in HT monthly newsletter and google poll to be set up 01.05.2024 It was agreed to progress this item in the next school term and to allow for PC social media to be set up in order to promote | https://mcusercontent.com/b9c117346e8204e58a48bb6f1/files/0c88861a-29c8-525c-b83c-2033ceaffaae/YSL_Leaflet_2021.pdf
PC16 | 06.03.2024 | Future Fundraising - PC requested to work with LT for 2024/25 planning of events (and required Lets) which incorporate fundraising in order to space out the financial cost to Parents/Carers | PC/LT | 05.06.2024 |  |  | LT to extend invitation to PC in June to progress 01.05.2024 LT agreed to meet with PC in June to progress and will provide date for this shortly
PC17 | 06.03.2024 | P7 Leavers - Discussion took place around the following: - P7 Hoodies - P7 Leavers mass/show - P7 event - Piper for last day | All | 05.06.2024 |  |  | The PC will contribute to the P7 leavers hoodies/food as per usual arrangements, (this will total £300) they will also decorate the balloon arches which can also be used for Nursery leavers and provide helium balloons - this will be done at start of last week of term in the gym hall. P7 leavers event - HT to discuss with P7 however, any out of school event similar to that of last year would be for parents to organise. P7 leavers normally leave on last day to all school in attendance and arch by P6 with music playing in the background, if a Piper was a parental request it would require to be funded and organised by them 01.05.2024 PC to provide above funding to HT as agreed along wit provision of balloons. Leavers events planned through HT inconjunction with P7 pupils. VC advised of one of the P7 parents looking into the potential of a Piper and will revert back at next meeting with an update
PC18 | 06.03.2024 | PC advised it is keen to pursue financial support through Tesco tokens and also potentially look into registering as a charity | PC | 05.06.2024 |  |  | Parent Council to contact Tesco and obtain paperwork to complete for charity registration 01.05.2024 NE made contact with Tesco Burnside and Tesco Dalmarnock. Both have differing process however, a letter is requied to be submitted with a structured request of the requirement for financial support to which there are 3 tiers, if chosen all of the tiers would need to be suitable for the request to allow Tesco to promote this should the request be chosen. The token promotion if chosen means you are visible in up to 10 stores. PC to seek further clarity on the application process and report back at next meeting
PC19 | 01.05.2024 | Parent Pay - discussion took place around utilising Parent Pay to allow Parents to pay online for PC events |  | 05.06.2024 |  |  | LT advised that Mrs McColgan is able to extract reports which would demostrate payment for events. PC to consider this option in the new school term
PC20 | 01.05.2024 | End of Term Raffle - discussion took place around LR proposal to facilitate an end of term raffle to help raise funds |  | 05.06.2024 |  |  | LR to contact Tunnocks / VC to contact Gladiators Basketball Team and NMcF to liaise with her workplace. A social media post is to be shared by the PC to enquire to seek raffle sponsors.

## Decision Log
Decision Rolling LOG: St Bride's School & Nursery Parent Council
A rolling action log is maintained of all actions arising or pending from each of the previous meetings. The status of Actions are categorised as follows:
Task complete - to be removed from listing
No identified risk, on target for completion date
Target completion date extended to allow flexibility
Target completion date unattainable, further explanation provided
Minute Ref | Meeting Date | Action | Action Owner | Due Date | Completion Date | BRAG status | Position Statement
PC12 | 06.03.2024 | PC Minutes - LT advised of recent parental feedback regarding visibility of PC monthly meeting discussions. PC proposed moving from a minutes template to that of a rolling action and decision log which can be updated within the meeting and shared within the PC update of the HTs monthly newsletter and be shared on school website, the group agreed to progress | PF | 01.05.2024 |  | Decision | PF to provided template for update 01.05.2024 Template shared, logos to be used on all future documentation
PC15 | 06.03.2024 | Maths Game Competition - Mr Nugent has requested prize funding support for the forthcoming Maths competition on 14.03.2024. The PC agreed to a £100 donation. |  | 01.05.2024 |  | Decision | JH to provide £100 to LT

## Closed Log
ROLLING Closed LOG: St Bride's School & Nursery Parent Council
A rolling action log is maintained of all actions arising or pending from each of the previous meetings. The status of Actions are categorised as follows:
Task complete - to be removed from listing
No identified risk, on target for completion date
Target completion date extended to allow flexibility
Target completion date unattainable, further explanation provided
Minute Ref | Meeting Date | Action | Action Owner | Due Date | Completion Date | BRAG status | Position Statement

## Attendees
ROLLING Closed LOG: St Bride's School & Nursery Parent Council
Name | Position | Meeting Date
|  | 06.03.2024 | 01.05.2024 | 05.06.2024 | TBC.09.2024 | TBC.10.2024 | TBC.11.2024 | TBC.12.2024
Louise Torrance (LT) | Head Teacher
Nicola Ewing (NE) | Parent Council Chair
Paula Frederick (PF) | Parent Council Chair
John Hylands (JH) | Parent Council Treasurer
Geraldine McAdam (GMcA) | Parent Council Secretary | Apologies | Apologies
Paula Jackson (PJ) | Parent Council
Laura Robertson (LR) | Parent Council
Bryan Lynch (BL) | Parent Council | Apologies | Apologies
Michelle Lynch (ML) | Parent Council | Apologies | Apologies
Vikki Campbell (VC) | Parent Council | Apologies
Claire Muldoon (CM) | Parent Council
Joanna Clark (JC) | Parent Council
Nicola McFadden (NMcF) | Parent Council